## Sheet1
2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25
Sprint 1 | [6 empty] | Sprint 2 | [6 empty] | Sprint 3
Focus: design | [6 empty] | Focus: prototype implementation | [6 empty] | Focus: prototype implementation
Tasks | [6 empty] | Tasks | [6 empty] | Tasks
Literature research: fall detection | [6 empty] | UI Design | [6 empty] | Sensortag: sensor data gathering
Mathematical model | [6 empty] | Sensortag: basic sensor data gathering | [6 empty] | Communication: Bluetooth connection
Definition of use cases | [6 empty] | Communication: basic Bluetooth connection | [6 empty] | PC application: data visualization
Component design | [6 empty] | PC application: basic data visualization | [6 empty] | Integration testing
Individual weekly reports | [6 empty] | Individual weekly reports | [6 empty] | Individual weekly reports
2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-02 | 2018-06-03 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-07 | 2018-06-08 | 2018-06-09 | 2018-06-10 | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15
Sprint 4 | [6 empty] | Sprint 5 | [6 empty] | Sprint 6
Focus: features implementation | [6 empty] | Focus: features implementation | [6 empty] | Focus: testing
Tasks | [6 empty] | Tasks | [6 empty] | Tasks
Additional features implementation | [6 empty] | Additional features implementation | [6 empty] | Final report
Performance testing | [6 empty] | Individual weekly reports | [6 empty] | Test statistics
Individual weekly reports | [13 empty] | Reliability testing
Individual weekly reports
2018-06-16 | 2018-06-17 | 2018-06-18 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22
Sprint 7
Focus: final report
Tasks
Final report